## Gantt Data
number | Task name | Duration (days) | Gregorian start date | Gregorian Expiry Date
1 | Project
2 | Introduction
3 | Overview of the course objectives and expectations | 2 | 2025-01-25 | 2025-01-26
4 | Explanation of the project selection process | 1 | 2025-01-26 | 2025-01-26
5 | Formation of project teams | 1 | 2025-01-27 | 2025-01-27
6 | Guidelines for preparing a project proposal | 3 | 2025-01-28 | 2025-01-30
8 | Feedback and revision of project proposals | 2 | 2025-02-01 | 2025-02-02
9 | Identification/Selection Project Idea | 3 | 2025-02-03 | 2025-02-05
10 | Project Introduction
11 | Choose a project title that is clear and reflects the project idea | 2 | 2025-02-06 | 2025-02-07
12 | Submission and presentation of project Introduction | 3 | 2025-02-08 | 2025-02-10
13 | Feedback and revision | 1 | 2025-02-11 | 2025-02-11
14 | System Analysis
15 | Introduction to requirements analysis techniques | 1 | 2025-02-12 | 2025-02-12
16 | Conducting interviews and surveys | 2 | 2025-02-13 | 2025-02-14
17 | Documenting user requirements (Functional & Non-functional) | 3 | 2025-02-15 | 2025-02-17
18 | System Development Requirements
19 | Environment and/or Tools (Software, Hardware, Utilities) | 2 | 2025-02-18 | 2025-02-19
20 | Use Case | 1 | 2025-02-20 | 2025-02-20
21 | Data Flow Diagram (Level 0 and 1) | 2 | 2025-02-21 | 2025-02-22
22 | Submission and presentation | 1 | 2025-02-23 | 2025-02-23
23 | Feedback and revision | 1 | 2025-02-24 | 2025-02-24
24 | System Design
25 | System Design Activity Diagram | 2 | 2025-02-25 | 2025-02-26
26 | System Design Sequence Diagram | 2 | 2025-02-27 | 2025-02-28
27 | Interface Design
28 | Logo | 2 | 2025-03-01 | 2025-03-02
29 | Style Guide (Typography and Color Palette) | 2 | 2025-03-03 | 2025-03-04
30 | Prototype | 4 | 2025-03-05 | 2025-03-08
31 | Database Design
32 | Entity Relationship Diagram (ERD) | 3 | 2025-03-09 | 2025-03-11
33 | Unified Modeling Language (UML) | 3 | 2025-03-12 | 2025-03-14
34 | System Development
35 | User Interface Development | 13 | 2025-03-15 | 2025-03-27
36 | Database Development | 5 | 2025-03-28 | 2025-04-01
37 | System Implementation and Maintenance
38 | System Implementation Procedure | 2 | 2025-04-01 | 2025-04-02
39 | System Testing (Purpose & Types) | 3 | 2025-04-03 | 2025-04-05
40 | System Maintenance (Purpose & Types) | 2 | 2025-04-06 | 2025-04-07
41 | Document Submission
42 | Submission of the final project documentation for Final | 3 | 2025-04-08 | 2025-04-10
45 | Defence and discussion of the project | 2 | 2025-04-15 | 2025-04-16